## Arkusz1
# | Topic-Area | Action | Responsible | Scheduled_at | Completed_at | COMMENTS | PDCA
1 | Status of actions from the last management review | Adapt the narrow fire-resistant room for mould storage (need to find a narrow trolley for mould transport + room cleaning) | Andrea Giannelli | 2026-11-15 |  | We are in the process of finding a suitable forklift. In the meantime, the room is to be cleaned. | D
2 | Status of actions from the last management review | Move the laboratory to the new room. | Artur Uciński | 2026-07-30 |  |  | P
3 | Status of actions from the last management review | Conduct a review of product families (per customer) and reduce measurement frequency in control plans where justified (based on non-conformance history and their costs – sorting, scrap) – to be completed this year if workload shows an upward trend | Artur Uciński | 2026-10-30 |  |  | P
4 | Status of actions from the last management review | Add a front guard to all metal pallets used for mould storage and transport – some pallets still to be completed this year | Andrzej Kalota | 2026-06-30 |  | Only a few metal pallets still missing. | D
5 | Contingency plan | Conduct a Contingency Plan review | Piotr Peresiak Andrea Giannelli Dariusz Jankowski | 2026-03-25 | 2026-03-24 | Contingency plan audit to be carried out according to the Quality yearly planning | A
6 | Contingency plan | Implement a fire detection system in hall 2. | Andrea Giannelli | 2026-07-30 |  |  | P
7 | Organization context | Provide the Staamp Group quality manager with information for updating the context resulting from this management review, as input to this year's Staamp context review and risk assessment for 2026 | Piotr Peresiak | 2026-03-28 | 2026-03-30 |  | A
8 | Quality management system | Define, test and implement LPA in each Staamp plant | Alessandro Finotello | 2026-12-15 |  |  | P
9 | Management process: turnover, cash flow, balance sheet | MQB4 assembly – robot deployment and replacement of manual inspection with automated inspection | Andrea Giannelli | 2026-12-15 |  |  | D
10 | Human resources: near miss | Conduct regular awareness training for employees on safety and workplace risks, and present the rationale and importance of near-miss event identification for improving workplace safety | Beata Bednarz | 2026-12-15 |  |  | P
11 | Quality: customer complaints | Develop a QIP for 2026 | Piotr Peresiak | 2026-06-30 |  |  | P
12 | Poor quality cost vs. Turnover | Analyse scrap rates and root causes in greenhouses B, C and D, and define an action plan to reduce scrap – monthly meetings | Piotr Peresiak Dariusz Jankowski | 2026-12-01 |  |  | D
13 | Production logistics: % cost special delivery vs. turnover | Prepare data analysis from weekly coverage-not-met meetings – Pareto of causes, Pareto of corrective actions taken, and develop an action plan to mitigate the most frequent causes reducing the coverage rate | Piotr Peresiak | 2026-05-30 |  |  | D
14 | Purchasing: % of A rating suppliers (+ ok if indirect material) | Supplier audit: FIXI | Alessandro Finotello | 2026-06-30 |  | Awaiting confirmation of the visit date | D

## Arkusz2
1 | P
2 | D
3 | C
4 | A